## BURNDOWN CHARTS
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#1 | User can create an account using a custom username and password | -Create and style the sign-up and sign-in forms -Configure Firebase and enable Email/Password authentication -Capture user input values from the sign-up form -Allow users to log in using their email and password | 2 | HIGH | HIGH - Core component of website | Liyan | 1
#2 | User can login into their account | -The login page was created. -The title, username, and password were added as labels. -Input fields for username and password were included. -A submit button for login was added. -A link to create an account is available for new users. -The design was adjusted by modifying colors, size, and placement. -A background was also added. | 2 | HIGH | HIGH - Core component of website | Prathiksha | 1
#3 | Admin can add a channel with a custom name | -Create UI for channel list -Add button to create channel -Add form to enter channel name -Show each channel that has been created -Store channels on Firestore database | 3 | HIGH | HIGH - Core component of website | Marco | 1
#4 | Admin can assign a user to one or many channels | -Dropdown or search field to select users -Assign button to add a user to a channel -Deassign button to remove a user from a channel | 2 | HIGH | HIGH - Core component of website | Sarah | 1
#5 | User can view his own channel | -When a user logs in, they can see a "My Channels" button. -Firestore updates the channel list in real-time. -If an admin removes or modifies a channel, the user sees the changes instantly. | 2 | MEDIUM | MEDIUM - component of website | Sarah | 1
#6 | User can log out of their account | -Create log out button -Redirect user to login page when user clicks on "logout" in drop down menu | 1 | CRITICAL | LOW-component of website | Alexia | 1
#7 | Admin has access to all channels | -Allow admins to view, edit, or delete channels -Set Firebase Firestore rules to allow admins to access all chat data | 2 | MEDIUM | MEDIUM - component of website | Marco and Liyan | 1
#27 | Set up CI / CD pipeline using Jasmine testing framework. | -Set up unit tests in project repository. -Set up workflow yml file. -Create github action to run tests on each push. | 5 | HIGH | HIGH - Core component of automated testing pipeline | Marco | 2
#8 | User can send messages in the text channel | -Implemented Channel chat area -Implemented function to get Channel name from firebase -Implemented function to get Username of user from firebase -Implemented sending messages in text channel functionality -Implemented function to save messages sent in chat -Implemented functionality to save messages to Firebase -Implemented function to display time that messages were sent -Implemented function to ensure that messages were displayed in chronological order | 2 | HIGH | HIGH - Core component of website | Alexia | 2
#9 | As an admin, I want to delete inappropriate messages in text channels, so that I can maintain a safe environ | -Implement admin only delete functionality -Integrate Firestore document deletion -Ensure delete button is only visible to admins in the template -Add confirmation dialog to prevent accidental deletions | 2 | HIGH | MEDIUM - Component of website | Liyan | 2
#10 | As a user, I want to send a private message to another user. | - Create a UI for starting and displaying direct messages. - Implement real-time message updates using Firebase. - Implement backend support for storing and retrieving private messages. | 3 | HIGH | HIGH - Core component of website | Sarah | 2
#11 | make chats between user private | -Modified channel-area.component.ts -Modified chanel-selector.component.ts -Tested to ensure good functionality | 2 | HIGH | MEDIUM - Component of website | Prathiksha | 2
|  |  | Difficulty Level (0,1,2,3,5,8) | Priority |  | Assign | Sprint
Assign