## BURNDOWN CHARTS
SPRINT 1 | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#1 | User can create an account using a custom username and password | -Create and style the sign-up and sign-in forms -Configure Firebase and enable Email/Password authentication -Capture user input values from the sign-up form -Allow users to log in using their email and password | 2 | HIGH | HIGH - Core component of website | Liyan | 1
#2 | User can login into their account | -The login page was created. -The title, username, and password were added as labels. -Input fields for username and password were included. -A submit button for login was added. -A link to create an account is available for new users. -The design was adjusted by modifying colors, size, and placement. -A background was also added. | 2 | HIGH | HIGH - Core component of website | Prathiksha | 1
#3 | Admin can add a channel with a custom name | -Create UI for channel list -Add button to create channel -Add form to enter channel name -Show each channel that has been created -Store channels on Firestore database | 3 | HIGH | HIGH - Core component of website | Marco | 1
#4 | Admin can assign a user to one or many channels | -Dropdown or search field to select users -Assign button to add a user to a channel -Deassign button to remove a user from a channel | 2 | HIGH | HIGH - Core component of website | Sarah | 1
#5 | User can view his own channel | When a user logs in, they can see a "My Channels" button. -Firestore updates the channel list in real-time. -If an admin removes or modifies a channel, the user sees the changes instantly. | 2 | MEDIUM | MEDIUM - component of website | Sarah | 1
#6 | User can log out of their account | -Create log out button -Redirect user to login page when user clicks on "logout" in drop down menu | 1 | CRITICAL | LOW-component of website | Alexia | 1
#7 | Admin has access to all channels | -Allow admins to view, edit, or delete channels -Set Firebase Firestore rules to allow admins to access all chat data | 2 | MEDIUM | MEDIUM - component of website | Marco and Liyan | 1
SPRINT 2
#27 | Set up CI / CD pipeline using Jasmine testing framework. | -Set up unit tests in project repository. -Set up workflow yml file. -Create github action to run tests on each push. | 5 | HIGH | HIGH - Core component of automated testing pipeline | Marco | 2
#8 | User can send messages in the text channel | -Implemented Channel chat area -Implemented function to get Channel name from firebase -Implemented function to get Username of user from firebase -Implemented sending messages in text channel functionality -Implemented function to save messages sent in chat -Implemented functionality to save messages to Firebase -Implemented function to display time that messages were sent -Implemented function to ensure that messages were displayed in chronological order | 2 | HIGH | HIGH - Core component of website | Alexia | 2
#9 | As an admin, I want to delete inappropriate messages in text channels, so that I can maintain a safe environ | -Implement admin only delete functionality -Integrate Firestore document deletion -Ensure delete button is only visible to admins in the template -Add confirmation dialog to prevent accidental deletions | 2 | HIGH | MEDIUM - Component of website | Liyan | 2
#10 | As a user, I want to send a private message to another user. | - Create a UI for starting and displaying direct messages. - Implement real-time message updates using Firebase. - Implement backend support for storing and retrieving private messages. | 3 | HIGH | HIGH - Core component of website | Sarah | 2
#11 | make chats between user private | -Modified channel-area.component.ts -Modified chanel-selector.component.ts -Tested to ensure good functionality | 2 | HIGH | MEDIUM - Component of website | Prathiksha | 2
SPRINT 3 |  |  | Difficulty Level (0,1,2,3,5,8) | Priority |  | Assign | Sprint
#12 | Implement Default and Private Channels | Admin should be able to create default public channels (e.g., #all-general) where all registered users can participate. Users should be able to create private channels and invite specific registered users to join. Users can leave channels or request to join a private channel. Implement UI elements to differentiate between public and private channels. | 8 | HIGH | HIGH - Core component of website | Prathiksha and Liyan | 3
#13 | Channel Management Features | Add functionality for channel owners to accept or decline join requests. Ensure that users cannot access messages of a private channel unless they have been accepted. Modify Firebase structure to store public and private channel information. Update UI to display available channels dynamically. | 5 | HIGH | HIGH - Core component of website | Prathiksha and Liyan | 3
#14 | I want to see real-time status indicators (Online, Offline, Away) for other users | Show online status for logged-in users. Mark users as "away" if inactive for a set duration. Mark users as "offline" when logged out. Last seen timestamp Users can send direct messages to users, even if they are not logged in Update Firebase with user presence status in real-time. Display user status on the dashboard. | 3 | LOW | LOW - Component of website | Sarah | 3
#15 | Implement Emoji Support | Integrate an emoji picker in the message input field. Ensure emojis are correctly displayed when sent and received. Store emojis as part of message content in Firebase. | 3 | LOW | LOW - Component of website | Alexia | 3
#16 | I want to be able to reply to messages in DM or channel text chat by quoting it. | User should click on "Quote" button to initiate reply. Quoted messages appears in reply. User can cancel reply. | 3 | LOW | LOW - Component of website | Marco | 3
SPRINT 4 | [5 empty] | Assign
#17 | As a user, I want to toggle between Light and Dark modes using a dedicated button, so that my theme preference is stored and remains consistent after logout and login. | Added a toggle button to switch between Light and Dark modes. User’s theme preference is stored Theme stays consistent after logout/login. | 3 | LOW | LOW - Component of website | Sarah | 4
#18 | As a user, I want to select a custom background color for my chat areas in both channels and direct messages, so that I can personalize my messaging experience. | Users can select a custom background color for each channel's chat area and direct messages area. -A color picker is shown in the channel UI to let users choose. -Color is saved per channel, using channelName as the unique key. -The color choice is stored, so it stays even after logout or page refresh. | 2 | LOW | LOW - Component of website | Alexia | 4
#19 | As a user or admin, I want an enhanced UI system with a modern, intuitive, and responsive design, so that I can navigate the application seamlessly and enjoy a consistent, efficient, and accessible user experience. | Fix message bubbles, because they all go to the left of the window. -Add different colors for messages (blue for sender and grey for recipient). -Add scrollable window for direct messaging and channel selection area. -Make font uniform across website. | 5 | HIGH | MEDIUM - Component of website | Liyan and Prathiksha | 4
#20 | As a user, I want to receive real-time notification messages from text channels and private messages when I'm mentioned, so that I can stay updated. I also want to view my notifications in order and have the ability to delete them when they're no longer needed. | Trigger a notification when a user is mentioned using @username in text channels or private messages. Deliver mention notifications in real-time. Allow users to delete individual notifications. Display notifications in chronological order, with the newest first. | 5 | HIGH | MEDIUM - Component of website | Sarah | 4